Name: Adam Nickle
	Current / Status	Start Date			Stop Date			Number of Hours
		Proposed	Modified	Actual	Proposed	Modified	Actual	Proposed	Modified	Actual
Proposal	Complete	-	-	Jan 09	Jan 11	-	Jan 11	5	-	6
Research	Started	Jan 11	-	Jan 11	-	-	-	35	90	89
Requirements	Started	Jan 11	-	Jan 11	Jan 11	Feb 27	Mar 13	15	10	9
Core Design	-	Jan 23	Feb 27	Mar 13	Feb 13	Apr 3	Jun 4	30	70	70
UI Design	-	Jan 30	Feb 6	Mar 13	Feb 17	Mar 27	Mar 27	20	10	12.5
Core Dev	-	Feb 17	Mar 27	May 15	Mar 20	Jun 19	Sep 11	15	65	59+15
Interface Dev	-	Mar 6	Mar 24	May 15	Mar 20	Jul 3	Sep 11	10	20	18
Core Test	-	Mar 6	Jul 3		Mar 27	Jul 10	Sep 17	10	15	11+12
Interface Test	-	Mar 20	Jul 3		Mar 27	Jul 10	Sep 11	6	6	5+2
System Test	-	Mar 27	Jul 10		Mar 31	Jul 13	Sep 17	8	10	+10
Demo Prep	-	Mar 27	Jul 10		Apr 2	Jul 17	Sep 26	3	3	+2
Demo	-	Apr 3	TBD		Apr 3	TBD	Sep 26	-	-
Total	-	-	-	-	-	-	-	157	299	320.5

Accomplishments / - Implemented FFT, IFFT, and bandpass filter. / -Worked out major kinks in the multi-threading approach. / - Fixed a major bug preventing the worker threads from finishing on time. / - Tested the program on several subjects, identifying pulse, breathing, and other periodic changes. / - Demonstrated the project in person; fulfilled all original requirements with one exception which was handled with a change request before the demonstration. / - Assembled remaining deliverables. / - Identified several possible directions to take this project in the future.
Problems / - Motivation, moving, and employment; I now have a new job and it took a lot of my time, both from my family and from this project. / - Neglected to deliver several status updates.
Changes in Scope, Schedule, and Cost / -Expected dates were never modified though they should have been.
Confessional / Increase: 41 / Status: Finished far behind schedule. / Total hours: 320.5
Scripture / Isaiah 1:18 / “Come now, and let us reason together, saith the Lord: though your sins be as scarlet, they shall be as white as snow; though they be red like crimson, they shall be as wool.”